## Data
Requirements Traceability
Project Name: |  |  | Thesis B
Project Description: |  |  | Testing webpage: www.extremedigital.hu
Requirements |  |  |  |  | Testing |  |  | Comment | Defects
Req. ID | Name | Requirements Description | Requirement Type | Test Condition | Test Description | Test steps | Priority | Comment | Defect ID | Defect Description
TC-01 | Registration | Success registration, or existing registragion alert result | Functional | Success | Opening webpage, navigating to registration page, fill the registration fields | 1. Open webpage 2. Click Account logo 3. Choosing registration menupoint. 4. Filling registration fields 5. Marking checkbox 6. Pushing Registration Button | Normal
TC-02 | Sign In | Success sign in | Functional | Success | Opening webpage, navigating to sign in page, fill the sign in fields | 1. Open webpage 2. Click Sign in link 3. Filling sign in fields 4. Pushing Sign in Button | Normal
TC-03 | Log Out | Succes Logging out and navigating Guest homepage | Functional | Success | Log out on webpage from account | 1. Open webpage 2. Logging In 3. Clicking on account logo 4. Choosing Log out point | Normal
TC-04 | Delete Data | Delete data from field | Functional | Success | Deleting Data from Billing | 1. Choosing mobile group 2. Choosing ebook group 3. Choosing a ebook 4. Clicking to cart button 5. Clicking away cart button 6. Choosing name field 7. Delete Data from name field | Normal
TC-05 | Rewriting Data | Rewriting Data in field | Functional | Success | Rewriting Data in Billing Page | 1. Choosing mobile group 2. Choosing ebook group 3. Choosing a ebook 4. Clicking to cart button 5. Clicking away cart button 6. Choosing name field 7. Rewriting Data from name field | Normal
TC- 06 | Listing data from webpage | Listing Data | Functional | Success | Listing Data From product | 1. Filling searchbar field 2. Collect Data from product | Normal
TC-07 | Listing from more sites | Listing Data with pagination | Functional | Success | Listing Data From products from more sites | 1. Filling searchbar field 2. Collect Data from product 3. Clicking next page 4. Repeating Data Collecting 5. Attain to last page | Normal
TC-08 | Saving Data from page in File | Saving Data from page in File | Functional | Success | Saving Data from page in File | 1. Signing In 2. Creating File 3. Write List Datas in File 4. Reading saved Datas from File | Normal

## Status
Req. ID | (Multiple Items)
Count of Req. Status | Requirement Type
Req. Status

## Requirements
Req. ID | Requirements Description
R1 | Item property
R2 | Hero property
R3 | Monster property
R4 | Door properties
R5 | Screen
R6 | Gameplay
R7 | Program usage

## decision tables and flowcharts
| Test1 | Test2
Could you move through the door? | y | n
Result | Door open | Door closed
| Test1 | Test2 | Test3 | Test4
The door is open? | y | n | y | n
Have you got a key? | n | n | y | y
Result | can move through | can not move trough | can move through | can move through

## BurnDownChart
Days | Taks (optimal) | Task (real) | tasklist | task name | Optimal date | Real date
0 | 64 | 61 | 1 | DEV meet 1 | 1 | 1
1 | 59 | 56 | 2 | DEV meet 2 | 2 | 2
2 | 44 | 42 | 3 | DEV meet 3 | 3 | 3
3 | 34 | 31 | 4 | DEV meet 4 | 4 | 4
4 | 30 | 27 | 5 | DEV meet 5 | 6 | 7
5 | 28 | 25 | 6 | DEV meet 6 | 7
6 | 19 | 19 | 7 | DEV meet 7 | 8
7 | 15 | 13 | 8 | DEV meet 8 | 9
8 | 5 | 8 | 9 | Tester meet 1 | 1 | 1
9 | 0 | 0 | 10 | Tester meet 2 | 2 | 2
|  |  | 11 | Tester meet 3 | 3 | 3
|  |  | 12 | Tester meet 4 | 4 | 4
|  |  | 13 | Tester meet 5 | 5 | 5
|  |  | 14 | Tester meet 6 | 6 | 6
|  |  | 15 | Tester meet 7 | 7 | 7
|  |  | 16 | Tester meet 8 | 8 | 8
|  |  | 17 | Tester meet 9 | 9 | 9
|  |  | 18 | Test plan | 1 | 1
|  |  | 19 | T.matrix | 2 | 2
|  |  | 20 | T.matrix back | 8 | 8
|  |  | 21 | Schedule | 1 | 1
|  |  | 22 | Summary report | 9 | 9
|  |  | 23 | Presentation | 9 | 9
|  |  | 24 | Test plan edit | 1 | 1
|  |  | 25 | Test plan edit II | 2 | 2
|  |  | 26 | Test plan edit III | 6 | 6
|  |  | 27 | Flowchart Laci | 2 | 2
|  |  | 28 | Flowchart M.Bálint | 2 | 2
|  |  | 29 | D.Table Bözse | 2 | 2
|  |  | 30 | V1 Test cases for Bözse in Excel | 2 | 2
|  |  | 31 | V1 Test cases for Laci in Excel | 2 | 2
|  |  | 32 | V1 Test cases for M.Bálint in Exce | 2 | 2
|  |  | 33 | V1 Test cases for N.Bálint in Exce | 2 | 2
|  |  | 34 | V1 Test cases for Dani in Excel | 2 | 2
|  |  | 35 | V1 Test cases for Bözse JIRA | 3 | 3
|  |  | 36 | V1 Test cases for Laci in JIRA | 3 | 3
|  |  | 37 | V1 Test cases for M.Bálint in JIRA | 3 | 3
|  |  | 38 | V1 Test cases for N.Bálint in JIRA | 3 | 3
|  |  | 39 | V1 Test cases for Dani in JIRA | 3 | 3
|  |  | 40 | Export Excel to Jira | 2 | 3
|  |  | 41 | Get working program | 3 | 3
|  |  | 42 | Burndown chart 2 | 2 | 2
|  |  | 43 | Burndown chart 3 | 3 | 3
|  |  | 44 | Burndown chart 4 | 4 | 4
|  |  | 45 | Burndown chart 5 | 5 | 5
|  |  | 46 | Burndown chart 6 | 6 | 6
|  |  | 47 | Burndown chart 7 | 7 | 7
|  |  | 48 | Burndown chart 8 | 8 | 8
|  |  | 49 | Burndown chart 9 | 9 | 9
|  |  | 50 | V1 Test execution Bözse | 6 | 6
|  |  | 51 | V1 Test execution MBálint | 6 | 6
|  |  | 52 | V1 Test execution NBálint | 6 | 7
|  |  | 53 | V1 Test execution Dani | 6 | 6
|  |  | 54 | V1 Test execution LAci | 6 | 7
|  |  | 55 | V2 Test execution Bözse | 8 | 8
|  |  | 56 | V2 Test execution MBálint | 8 | 9
|  |  | 57 | V2 Test execution NBálint | 8 | 9
|  |  | 58 | V2 Test execution Dani | 8 | 9
|  |  | 59 | V2 Test execution LAci | 8 | 9
|  |  | 60 | Review documents 2 | 2 | 2
|  |  | 61 | Review documents 3 | 3 | 3
|  |  | 62 | Review documents 4 | 4 | 4
|  |  | 63 | Review documents 5 | 7 | 7
|  |  | 64 | Review documents 6 | 8 | 8
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100